## Sheet1
Defect ID | Defect Reporting Date | Project Name | Project Version | Module / Sub Module Name | Type of Defect | Phase | Summary | Description | Severity | Priority | Status | Reported By | Reported To
DF01 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Add Item | Wrong | System | For Add Item minimum 1 quantity is required but it allows to add the item with 0 quantity. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "Please enter quantity, quantity should not be kept blank". Actual :- system is not displaying error message and it allows to add the item with 0 quantity. | Low |  | New | Sakshi Rane | Rajani Sankpal
DF02 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Add Item | Wrong | System | The price must not be 0 when adding the item. However, the item ends up being added to the list with a price of 0. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- "System should display error message "Please enter price, price should not be 0". Actual :- system displays the warning message "Price 0.00 is below Standard Cost 776.18" but item gets add in the list | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF03 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Add Item | Wrong | System | It shows an error message only for the Price field, but all fields are left blank, it should indicate that all fields are mandatory. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "Required fields should not be blank." Actual :- system displays the warning message "Price 0.00 is below Standard Cost 776.18" but it should display error message for other field also | Low |  | New | Sakshi Rane | Rajani Sankpal
DF04 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Update Item | Wrong | System | Shipping charges should always be a positive amount, yet it is currently allowing negative values and updating the amount in Total Amount. | Steps :- Add Item -> Enter Shipping Charge -> Click -> Update Expected :- System should display error message "Shipping charge can not be less than 0." Actual :- system is not displaying any error message and amount gets update according to mentioned shipping cost | Low |  | New | Sakshi Rane | Rajani Sankpal
DF05 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Update Item | Wrong | System | Shipping cost amount is valid upto $50 and yet it allows to add shipping charge greater than 50 | Steps :- Add Item -> Enter Shipping Charge -> Click -> Update Expected :- System should display error message "Shipping charge should not be more than $50." Actual :- system is not displaying any error message and amount gets update according to mentioned shipping cost | Low |  | New | Sakshi Rane | Rajani Sankpal
DF06 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Delivery Details | Wrong | System | Delivery details must be essential for placing the quotation since the quotation get placed without delivery details | Steps :- Select Payment Mode -> Cash Only -> select Delivery from Location Expected :- System should display error message "Delivery from Location field is required." Actual :- system is not displaying any error message and the quotation gets place without delivery details | Low |  | New | Sakshi Rane | Rajani Sankpal
DF07 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Delivery Details | Wrong | System | The address field must be filled in to submit the quotation, yet it accepts the submission of the quotation without an address. | Steps :- Select Payment mode -> (Due15th of Following month, Due by end of Following month, Payment due Within 10 days) -> Select Delivery from Location-> Enter Valid until -> Deliver to ->Address-> contact no-> Customer Reference -> Comments ->Select Shipping Company Expected :- System should display error message "You should enter the street address in the box provided. Orders cannot be accepted without a valid street address." Actual :- system is not displaying any error message and it is placing the quotation of sales successfully without Address | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF08 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Delivery Details | Wrong | System | delivery from location, valid until, deliver to, address this fields are required for delivery details but it shows error message only for deliver to field | Steps :- Select Payment mode -> (Due15th of Following month, Due by end of Following month, Payment due Within 10 days) -> Select Delivery from Location-> Enter Valid until -> Deliver to ->Address-> contact no-> Customer Reference -> Comments ->Select Shipping Company Expected :- system should display error message "Please enter required fields of Quotation Delivery Details for further processing" Actual :- system is displaying error message but only for Deliver to field it is not displaying error message for rest of the fields | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF09 | 2025-06-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Delivery Details | Wrong | System | In prepaid we have to pay full amount but it is allowed to mention less amount than total amount for pre paid field | Steps :- Select Payment mode -> Prepaid -> Select Delivery from Location-> Enter Valid until -> Deliver to ->Address-> contact no-> Customer Reference -> Comments ->Select Shipping Company Expected :- system should display error message "Pre-payment amount is less than Total amount or you mentioned only 50% of Total amout. " Actual :- system is not displaying any error message and it allows to place the sales quotation with less amount than total amount for prepaid | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF10 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Date | Wrong | System | Selecting a past date for the quotation date is accepted, but when a past date is chosen, it is highlighted in red. However, the quotation get placed with past date | Steps :- Select Quotation Date -> Add Item -> Fill Delivery Details -> Place Quotation Expected :- past date should be accepted for quotation Actual :- the date is highlighted in red color but quotation gets placed | Low |  | New | Sakshi Rane | Rajani Sankpal
DF11 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Date | Wrong | System | A future date is not permitted for the quotation date. However, the date is highlighted in red, and the quotation is created with the future date. | Steps :- Select Quotation Date -> Add Item -> Fill Delivery Details -> Place Quotation Expected :- system should display error message along with highlight the date in "RED" color "The date should not be future date" Actual :- the date is highlighted in red color but system is not displaying any error message and it also allows to place the quotation | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF12 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Quotation - Quotation Delivery Details - "Valid Until" | Wrong | System | The quotation is only supposed to be valid for one day, but it accepts validity dates that extend beyond that date and, quotation is being placed with future date that exceed one day. | Steps :- Select Quotation Date -> Add Item -> Select Valid Until -> Place Quotation Expected :- future date should be accepted for quotation validation(expiration) but upto 1 day. "Quotation should get invalid after passing of 1 day." Actual :- A future date is allowed, but only for a single day. However, validation for quotations permits more than one day. | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF13 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Quotation - Edit Item | Wrong | System | The quantity and price fields should not be left blank, yet they still allow blank entries during editing, and only displaying a warning message. | Steps :- Add Item -> Click on Edit -> Edit required fields -> click Save Expected :- System should display error message "Price 0.00 is below Standard Cost 15.48" Actual :- warning message gets display but blank i.e. 0 gets updated in editable field | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF14 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Order - Order Date | Wrong | System | The order date for a sales order cannot be a future date, yet the system is allowing future order dates and is also processing orders with those dates. | Steps :- Select Order Date -> Add Item-> Click on Place Order Expected :- system should display error message along with highlight the date in "RED" color "The date should not be future date" Actual :- date gets highlighted in red color but order gets placed with future date | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF15 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Order - Order Date | Wrong | System | Selecting a past date for the order date is accepted, but when a past date is chosen, it is highlighted in red. However, the order get placed with past date | Steps :- Select Order Date -> Add Item-> Click on Place Order Expected :- past date should be accepted for order date Actual :- date gets highlight in red color but order gets place | Low |  | New | Sakshi Rane | Rajani Sankpal
DF16 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Order - Delivery Date | Wrong | System | The order date and delivery date should not be the same; however, the system allows placing the order with same dates for order and delivery. | Steps :- Select Delivery Date -> Add Item-> Click on Place Order Expected :- system should display error message "Select a delivery date that comes after the chosen order date." Actual :- order date and delivery date for same day not possible but it allows to place the order | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF17 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Order - Add Item | Wrong | System | For Add Item minimum 1 quantity is required but it allows to add the item with 0 quantity. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "Please enter quantity, quantity should not be kept blank" Actual :- system is not displaying error message & it allows to add the item with 0 quantity. | Low |  | New | Sakshi Rane | Rajani Sankpal
DF18 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Order - Add Item | Wrong | System | The price must not be 0 when adding the item. However, the item ends up being added to the list with a price of 0. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "Please enter price, price should not be 0" Actual :- system displays the warning message "Price 0.00 is below Standard Cost 776.18" but item gets add in the list | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF19 | 2025-07-03 | Front Accounting | 2.4.15 | Sales Order - Add Item | Wrong | System | It shows an error message only for the Price field, but all fields are left blank, it should indicate that all fields are mandatory. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "Required fields should not be blank." Actual :- system displays the warning message "Price 0.00 is below Standard Cost 776.18" but it should display error message for other field also | Low |  | New | Sakshi Rane | Rajani Sankpal
DF20 | 2025-07-03 | Front Accounting | 2.4.15 | Deliver Items for Sales order - Date | Wrong | System | Selecting a past date for the deliver items date is not accepted, but when a past date is chosen, it is highlighted in red. However, items get dispatched with past date | Steps :- Select Date -> click on Process Dispatch Expected :- past date should be not be accepted Actual :- system displays the date in red color but it allows the past date to dispatch the items | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF21 | 2025-07-03 | Front Accounting | 2.4.15 | Deliver Items for Sales order - Date | Wrong | System | A future date is not permitted for the date. However, the date is highlighted in red, and the process for items get dispatched with the future date. | Steps :- Select Date -> click on Process Dispatch Expected :- system should display error message along with highlight the date in "RED" color "The date should not be future date" Actual :- system displays the date in red color but it allows the future date | Low |  | New | Sakshi Rane | Rajani Sankpal
DF22 | 2025-07-03 | Front Accounting | 2.4.15 | Deliver Items for Sales order - Invoice Date | Wrong | System | An invoice deadline cannot be set for a past date since it must be allow before the chosen payment date | Steps :- Select Date-> Select Invoice Date-> click on Process Dispatch Expected :- past date should not be accepted for invoice deadline and date should be highlighted in red color Actual :- date is not highlighting in red color and it accepts the past date | Low |  | New | Sakshi Rane | Rajani Sankpal
DF23 | 2025-07-03 | Front Accounting | 2.4.15 | Deliver Items for Sales order - Invoice Date | Wrong | System | invoice deadline is valid according to the payment method like if payment mode is due within 10 days then invoice is vailid upto 10 days after that the invoice gets expired. However, system allows after 10 days also to select the invoice deadline which is not acceptable | Steps :- Select Date-> Select Invoice Date-> click on Process Dispatch Expected :- invoice deadline is according to the payment method we select - eg. due within 10 days then the date should valid upto 10 days after that invoice deadline should get invalid Actual :- even if the date is selected after 10 days it is allowing to accept date after 10 days and it also does not highlight the date in red color | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF24 | 2025-07-03 | Front Accounting | 2.4.15 | Deliver Items for Sales order - Process Dispatch | Wrong | System | once the process has been dispatched for selected items and again we go back to same delivery item page - the page should get refresh. However, the data does not get refresh and previous item list get shown with error message. | Steps :- Select Date-> Select Invoice Date-> Edit quantity -> select Action for balance -> click on Process Dispatch Expected :- system should display message "This page can only be opened if an order or delivery note has been selected. Please select it first." and page should get refresh Actual :- system shows error message but the page is not refreshing | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF25 | 2025-07-03 | Front Accounting | 2.4.15 | Issue Invoice for Delivery - Due Date | Wrong | System | due date should not be previous date than that mentioned invoice date however, it accepts the past due date and invoice get processed | Steps :- Select Due Date-> click on Process Invoice Expected :- if the due date is selected before the mentioned invoice date, system should display error message "The date mentioned is before the invoice date" Actual :- past date mentioned in due date and system accepts this past date which should not be accepted and invoice get issue for order | Low |  | New | Sakshi Rane | Rajani Sankpal
DF26 | 2025-07-03 | Front Accounting | 2.4.15 | Issue Invoice for Delivery - Due Date | Wrong | System | the due date is associated with payment term which we selected - according to mode of payment current date is not acceptable for due date. However, it allows the current date and invoice also get processed. | Steps :- Select Due Date-> click on Process Invoice Expected :- if the due date is selected is same as current date but according to payment method - due within 10 days then the due date should be 10 days after invoice date Actual :- the invoice gets issued but according to payment term - the date is current date which is not valid to be processed the invoice | Low |  | New | Sakshi Rane | Rajani Sankpal
DF27 | 2025-07-03 | Front Accounting | 2.4.15 | Issue Invoice for Delivery - Invoice Items | Wrong | System | In the invoice items, the quantity field is the only field that can be edited. however, the 'Item Description' field is also editable, and when the update button is clicked, the description gets updated as well. | Steps :- Edit This Invoice -> click on Update Expected :- only quantity and shipping cost should updated when click on update, rest fields are non editable Actual :- "Item description field is editable & when it gets edited -> click on update -> the item description also get update" | Low |  | New | Sakshi Rane | Rajani Sankpal
DF28 | 2025-07-03 | Front Accounting | 2.4.15 | Purchase Order Entry - Order Date | Wrong | System | The order date should only be current date. However, the system allows orders to be placed using past date. | Steps :- Select order date -> Add Item-> click on Place Order Expected :- system should display error message along with highlight the date in "RED" color "The date should not be past date" Actual :- past date gets accepted and order gets placed only the date gets highlight in red color | Low |  | New | Sakshi Rane | Rajani Sankpal
DF29 | 2025-07-03 | Front Accounting | 2.4.15 | Purchase Order Entry - Order Date | Wrong | System | The order date should only be current date. However, the system allows orders to be placed using future date. | Steps :- Select order date -> Add Item-> click on Place Order Expected :- system should display error message along with highlight the date in "RED" color "The date should not be past date" Actual :- future date gets accepted and order gets placed only the date gets highlight in red color | Low |  | New | Sakshi Rane | Rajani Sankpal
DF30 | 2025-07-03 | Front Accounting | 2.4.15 | Purchase Order Entry - Add Item | Wrong | System | price should not be 0 while adding the item in the list. however, it still allows to add 0 price while adding the item in the list. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "The price entered must be numeric and not less than zero.". Actual :- system does not display any error message and item gets add with 0 price in the list | Low |  | New | Sakshi Rane | Rajani Sankpal
DF31 | 2025-07-03 | Front Accounting | 2.4.15 | Purchase Order Entry - Add Item | Wrong | System | price and quantity should not be blank while adding the item in the list. However, it allows to add the price and quantity with 0 value in the list. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "The price entered must be numeric and not less than zero." & "The quantity of the order item must be numeric and not less than 1". Actual :- system displays error message but only for quantity and not for other fields | Low |  | New | Sakshi Rane | Rajani Sankpal
DF32 | 2025-07-03 | Front Accounting | 2.4.15 | Purchase Order Entry - Add Item | Wrong | System | price and quantity should not be negative while adding the item in the list. However, it displays the error message only for quantity and not for price. | Steps :- Select Item Code ->Item Description Enter Price ->Quantity Click -> Add Item Expected :- System should display error message "The price entered must be numeric and not less than zero." & "The quantity of the order item must be numeric and not less than 1". Actual :- system displays error message but only for quantity and not for other fields | Low |  | New | Sakshi Rane | Rajani Sankpal
DF33 | 2025-07-03 | Front Accounting | 2.4.15 | Receive Purchase Order Items - Items to Receive (Update) | Wrong | System | when negative quantity gets add in This Delivery and click on update. The system does not show any error message and after updating the value in this devliery gets converted to 0. | Steps :- Edit This Delivery -> click on update Expected :- system should display error messsage "There is nothing to process. Please enter valid quantities greater than zero." Actual :- system does not show any error message when negative quantity gets add, while updating it only update quantity field to 0. | Low |  | New | Sakshi Rane | Rajani Sankpal
DF34 | 2025-07-03 | Front Accounting | 2.4.15 | Receive Purchase Order Items - Process Receive Items | Wrong | System | click on Process Receive items -> click on Back-> the page get redirect to Receive Purchase order items and again click on Process Receive Items the page should get refresh but instead of that the previous entries get displayed. | Steps :- Edit This Delivery -> click on update-> click on Process Receive Items Expected :- The page should get refresh & message should shown "There is nothing to process. Please enter valid quantities greater than zero." Actual :- system shows the error message but page is not get refresh | Medium |  | New | Sakshi Rane | Rajani Sankpal
DF35 | 2025-07-03 | Front Accounting | 2.4.15 | Enter Supplier Invoice - Update | Wrong | System | the tax price can not be negative. however, when negative tax price gets enter the total amount gets update with negative tax price | Steps :- Click on Add Item -> Enter Tax -> click on update Expected :- system should display error message "Tax price should not be less than 0" Actual :- the total amount gets update and negative tax price gets applied in total amount | Low |  | New | Sakshi Rane | Rajani Sankpal
DF36 | 2025-07-03 | Front Accounting | 2.4.15 | Inventory Location Transfers - Date | Wrong | System | past date is acceptable while proccessing but date gets highlight in red color | Steps :- Select Date -> click on add item -> click Process Transfer Expected :- past date should be accepted for date Actual :- the date is highlight in red color but it should accept the past date | Low |  | New | Sakshi Rane | Rajani Sankpal
DF37 | 2025-07-03 | Front Accounting | 2.4.15 | Inventory Location Transfers - Date | Wrong | System | future date is not acceptable when proceesing the tranfer of inventories. However, it accepts the future date | Steps :- Select Date -> click on add item -> click Process Transfer Expected :- system should display error message along with highlight the date in "RED" color "The date should not be future date"" Actual :- system is not displaying any error message and date is highlighted in red color along with inventory items gets process with future date | Low |  | New | Sakshi Rane | Rajani Sankpal